## Tasks
User Story | Task Number | Name | Dependency | Story Points | Description
7 | 33 | Create code review strategy |  | 2 | Create skelton for code review strategy, should include the guidelines which team will refer to
7 | 34 | Review meeting vedio | 33 | 2 | Record the vedios for code review debriefing meeting and combine them into one vedio.
1 | 35 | Validate entity classes for newcomer and services |  | 2 | Create Unit Test suite for entity classes designed for Needs Assessment and Referrals Service
1 | 36 | Embedded mongoDB |  | 1 | Add dependency for embedded mongoDB: flapdoodle
6 | 37 | Test cases for db services | 36 | 5 | Create an embedded mongoDB instance when testing database CURD services. Create unit test suite for database services
7 | 38 | Test cases for CellError and ValueTranslator |  | 1 | Create unit test suite for loader classes, using mock file template
7 | 39 | Test cases for checker |  | 1 | Create unit test suite for checker classes
6 | 40 | Unit test cases for loader | 36 | 1 | Create unit test suite for loader classes
6 | 41 | Test cases for template reader |  | 2 | Create unit test suite for loader classes, using mock file template
3 | 42 | Integration/UAT test for user login | 35,36 | 5 | Create test suites using RestTemplate or MockMvc to automate testing for user login features
6 | 43 | UAT for file upload | 36,38,39,40,41 | 5 | Create UAT test suites using MockMvc or RestTemplate to test file upload feature. Should test over mock objects and real templates
9 | 42 | Integration/UAT test for report generation | 36,37 | 13 | Try to create integration/UAT test suite using MockMvc or RestTemplate to automate testing for report generation feature. If cannot find proper way to automate the validation process, then create documents for manually UAT processes. Each report should be tested
This sprint will focus mainly on Verification and Validation of our product. Hence, a lot of tasks that we have written involve creating unit, integration, and UAT tests for parts of the product that do not already have them. Moreover, we plan our conducting our code review during this sprint, so we will need to design a code review guideline and produce a video, based on recommendations that we came up with during the code review meeting for our product.

## Plan
User Stories | Tasks | Dependency | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7
7 | 33 |  | 2 | 1: Gurpreet:1; 2: Gurpreet:1
7 | 34 | 33 | 2 | 3: Gurpreet:1; 4: Gurpreet:1
1 | 35 |  | 2 | 1: Jerry:2
1 | 36 |  | 1 | 1: Michael: 1
6 | 37 | 36 | 5 | 2: Jerry:2; 3: Jerry:2; 4: Jerry:1
7 | 38 |  | 1 | 1: Jacob:1
7 | 39 |  | 1 | 1: Jacob:1
6 | 40 | 36 | 1 | 2: Michael: 1
6 | 41 |  | 2 | 2: Jacob:2
3 | 42 | 35,36 | 5 | 3: Michael: 1; 6: Michael: 2; 7: Michael: 2
6 | 43 | 36,38,39,40,41 | 5 | 4: Jerry:1; 5: Jerry:2; 7: Jerry:2
9 | 44 | 36,37 | 13 | 3: Jacob:1; 5: Jacob:2; 6: Jacob:2; 7: Jacob:2
Our plan focuses mainly on completing tasks that involve Verification and Validation. The rest of the user stories (13 and onwards, as well as ones we have placed lower priority on) will be given attention after this sprint, as they are smaller features that will not require as much time. Looking at task 9 in our plan, we know that it will take a long time to complete, so it will likely carry over to the next sprint as well.

## Execution
User Stories | Tasks | Dependency | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7
7 | 33 |  | 2 | 1: Gurpreet:1; 2: Gurpreet:1
7 | 34 | 33 | 2 | 3: Gurpreet:1; 4: Gurpreet:1
1 | 35 |  | 2 | 1: Jerry:2
1 | 36 |  | 1 | 2: Jerry:1
6 | 37 | 36 | 5 | 2: Jerry:2
7 | 38 |  | 1 | 1: Jacob:1
7 | 39 |  | 1 | 1: Jacob:1
6 | 40 | 36 | 1 | 3: Michael: 1
6 | 41 |  | 2 | 3: Jerry:1; 4: Jerry:1
3 | 42 | 35,36 | 5 | 5: Jerry:3; 6: Jerry:3
6 | 43 | 36,38,39,40,41 | 5 | 7: Jerry:3
9 | 44 | 36,37 | 13 | 3: Jacob:2; 7: Jacob:1
In our execution of this sprint, we managed to accomplish most of what we wanted to for the Validation and Verification of our product. The test coverage for our product is at 87.9%, and we have automated UAT testing for stories 1-7. Although as we anticipated, not every task in this sprint has been completed, so we will try to get those tasks done in the next sprint.

## Burndown Chart
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 34 | 29 | 24 | 24 | 17 | 17 | 17 | 7
Actual | 34 | 30 | 22 | 21 | 17 | 17 | 12 | 7
Overall, we managed to stay ahead of our plan in terms of tasks completed for this sprint. We had anticipated that not all tasks would be completed in this sprint, and we followed our sprint plan accordingly, with some variation in our execution. The tasks that were not completed in this sprint will be shifted to Sprint 5.