## Tasks
User Story | Task Number | Name | Dependency | Story Points | Description
13 | 51 | REST mapping for adding new account feature |  | 2 | Create a REST endpoint for adding new accout feature in dashboard controller. The method should only create a new account when all the parameters are valid.
13 | 52 | Exceptions for invalid parameter |  | 1 | Create an exception which will be thrown when any of the given parameters is not valid.
13 | 53 | Exception for used email |  | 1 | Create an exception which will be thrown when the given email is already used by another user.
13 | 54 | Global Exception handler | 52,53 | 3 | Create an exception handler classs for created exceptions so that the controller can catch the the exceptions and perform corresponding redirection.
13 | 55 | Error/Success message for user creating |  | 2 | Update the front-end to display a message about the result of creating a new user - succeed or failed.
13 | 56 | UAT for creating new accout feature |  | 2 | Create UAT cases using MockMVC to test creating new account feature.
16 | 57 | Change style of dashboard for Charlie |  | 2 | Use welcome page as a reference, re-organize the grouping of the report generation and user creation buttons for user Charlie.
16 | 58 | Enable Charlie to generate reports as Bob |  | 2 | Adjust the front-end and back-end so that Charlie, as a UTSC staff, can also generate reports as TEQ staff.
17 | 59 | Enable Charlie to create new account as Bob |  | 2 | Adjust the front-end and back-end so that Charlie, as a UTSC staff, can also generate reports as TEQ staff.
17 | 60 | Adjust the link in the navigation bar of dashboard |  | 1 | Change the link in the "weCare" button in the navigation bar of the dashboard from welcome page to dashboard.
8 | 61 | Make value translator be more error tolerant |  | 2 | Adjust ValueTranslator class so that it can accept certain kind of errors that can be fixed automatically (e.g. letter cases)
6 | 62 | Change style of result display page |  | 2 | Use welcome page as a reference, re-organize the grouping of the result display page for Alice using html table.
6 | 63 | Fix bugs in file type and file size in file upload. |  | 1 | Update application property file to increate the size limit of uploading file. Adjust template reader class to catch the error caused by non-excel file.
17 | 64 | Demonstration video for whole project |  | 3 | Create a 3-minite video for the project. Focusing on file upload and report generation features.
For our sprint 6, we plan to finish off any small tasks that we have left, including polishing off the front end and exception handling, as well as fixing any errors that we have found. We are nearing the end of the project, and if we remain on task then we should be on our way to presenting our final finished product.

## Plan
User Stories | Tasks | Dependency | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7
13 | 51 |  | 2 | 1: Jerry:2
13 | 52 |  | 1 | 1: Jacob:1
13 | 53 |  | 1 | 1: Jacob:1
13 | 54 | 52,53 | 3 | 2: Jerry:2; 3: Jerry:1
13 | 55 |  | 2 | 1: Michael:1; 2: Michael:1
13 | 56 |  | 2 | 1: Gurpreet:1; 2: Gurpreet:1
16 | 57 |  | 2 | 2: Jacob:2
16 | 58 |  | 2 | 3: Jacob:1; 4: Jacob:1
17 | 59 |  | 2 | 3: Michael:1; 4: Michael:1
17 | 60 |  | 1 | 3: Gurpreet:1
8 | 61 |  | 2 | 5: Jacob:1; 6: Jacob:1
6 | 62 |  | 2 | 5: Jerry:1; 7: Jerry:1
6 | 63 |  | 1 | 7: Jerry:1
17 | 64 |  | 3 | 6: Gurpreet:2; 7: Gurpreet:1
We have assigned tasks accordingly for members based on the features/exceptions/bug fixes that are left to make, and we will try to follow the plan as closely as possible as this is the last sprint.

## Execution
User Stories | Tasks | Dependency | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7
13 | 51 |  | 2 | 1: Jerry:1
13 | 52 |  | 1 | 1: Jerry:0.5
13 | 53 |  | 1 | 1: Jerry:0.5
13 | 54 | 52,53 | 3 | 2: Jerry:2; 3: Jerry:1
13 | 55 |  | 2 | 1: Michael:1; 2: Michael:1
13 | 56 |  | 2 | 2: Jacob:2
16 | 57 |  | 2 | 2: Gurpreet:1; 3: Gurpreet:1
16 | 58 |  | 2 | 4: Jacob:2
17 | 59 |  | 2 | 5: Jacob:2
17 | 60 |  | 1 | 5: Jerry:1
8 | 61 |  | 2 | 5: Jacob:1; 6: Jacob:1
6 | 62 |  | 2 | 5: Jerry:1; 6: Jerry:1
6 | 63 |  | 1 | 6: Jerry:1
17 | 64 |  | 3 | 6: Gurpreet:2; 7: Gurpreet:2
In the execution of the sprint, we managed to stay on task, with a few exceptions where we slightly over and underestimated some tasks, which is fine. Overall, we managed to prepare our product just as we’d hoped, and we highlighted the features we think the client would like in our video as per our discussion with team members and TA.

## Burndown Chart
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 26 | 22 | 16 | 12 | 8 | 8 | 6 | 0
Actual | 26 | 22 | 18 | 13 | 11 | 8 | 3 | 0
As explained in our execution, we managed to closely follow our sprint plan and complete the tasks we thought were necessary in the delivery of our final product. This was especially important for the final sprint since we needed to polish anything that was left undone (i.e. styling or error handling) so that we present everything we have been working towards since the start of the project.