## Tasks
User Story | Task Number | Name | Dependency | Story Points | Description
1 | 44 | Update front-end style for welcome page |  | 5 | Use new template to update our welcome page to make it look presentable
1 | 45 | Re-organize text and login buttons on welcome page | 44 | 2 | Add description for welcome page, and a small description for the main features of the product
1 | 46 | Update front-end for login page |  | 5 | Use template to clean up our login page to make it look presentable
4 | 47 | Change style of upload template page for Alice | 44 | 3 | Use welcome page as a reference, re-organize the grouping of the file upload buttons for user Alice
2 | 48 | Change the style of the report generation page for Bob | 44 | 3 | Use welcome page as a reference, re-organize the grouping of the file generation and user creation buttons for user Bob
13 | 49 | Set up the user-creation feature page for Bob | 48 | 4 | Create a page for Bob that allows him to create new users on behalf of others
3 | 50 | Re-factor code to follow appropriate design principles |  | 8 | Use feedback from our code-review guidelines, as well as from TA, to refactor some of the codebase
This sprint will focus mainly on improving our front-end design. As our project approaches completion, from our TA meeting we have concluded that we have sufficient features to present to the client. However, our front-end is severely lacking in design, which the client will not find appealing. Thus, the main focus of this sprint will to greatly improve the style of our welcome, login, and dashboard pages.

## Plan
User Stories | Tasks | Dependency | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | 44 |  | 5 | 1: Jacob: 3; 2: Jacob: 2
1 | 45 | 44 | 2 | 2: Michael: 2
1 | 46 |  | 5 | 1: Gurpreet: 1; 2: Gurpreet: 2; 3: Gurpreet: 2
4 | 47 | 44 | 3 | 2: Jacob: 1; 3: Jacob: 1; 4: Jacob: 1
2 | 48 | 44 | 3 | 2: Jerry: 2; 3: Jerry: 1
13 | 49 | 48 | 4 | 4: Jacob: 2; 5: Jacob: 2
3 | 50 |  | 8 | 4: Jerry: 1; 5: Jerry: 1; 6: Jerry: 1; 7: Jerry: 1
Our plan focuses mainly on completing tasks that involve the front-end design. If we have time in this sprint, we will try to redirect some of our at refactoring the codebase in accordance to TA feedback as well as our code review meeting, however this will likely be pushed to the next sprint, where we will make our final touches to the product.

## Execution
User Stories | Tasks | Dependency | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | 44 |  | 5 | 1: Jacob: 5
1 | 45 | 44 | 2 | 1: Michael: 1; 2: Michael: 1
1 | 46 |  | 5 | 2: Gurpreet: 2; 3: Gurpreet: 2; 4: Gurpreet: 1
4 | 47 | 44 | 3 | 1: Jerry: 2; 2: Jerry: 1
2 | 48 | 44 | 3 | 2: Jerry: 3
13 | 49 | 48 | 4 | 2: Jacob:2; 3: Jacob: 2
3 | 50 |  | 8 | 4: Jerry: 1; 5: Jerry: 1; 6: Jerry: 1
In our execution of this sprint, we managed to implement clean templates that greatly enhanced the design of our product, and we tried to do this as soon as possible so other team members can adjust the styling of pages that have been updated. We have started looking at implementing the different design patterns in our files (Singleton and template method) and will continue to do so in the next sprint.

## Burndown Chart
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 30 | 30 | 23 | 15 | 12 | 8 | 8 | 8
Actual | 30 | 25 | 17 | 13 | 8 | 8 | 8 | 8
Overall, we managed to stay on-plan throughout the sprint. The biggest concern was implementing the new template to our front-end, which we managed to complete very early on in the sprint. This set the foundation for improving smaller parts of the design such as the layout of text or buttons, which we worked on throughout the week. Also, we have started on our code refactoring, and we hope to finish it completely in the final sprint.