## Sheet1
User Story | Task Number | Name | Dependency | Story Points | Description
6 | 12 | Integrate an Excel Processor to the codebase |  | 2 | Add dependency for Apache POI file processor
6 | 13 | Design database for newcomer |  | 5 | Design mangodb database for newcomer information and service information
6 | 14 | Document classes for newcomer and services | 13 | 3 | Implement Entity classes required to store data in Needs Assessment and Referrals Service
6 | 15 | Design file process logic | 13 | 5 | Design packages/classes structure for file process following SOLID design pattern
6 | 16 | Create method for template recognition | 12 | 1 | Implement a method which takes in a excel file and return the type of the file
6 | 17 | Read data from template | 12 | 2 | Create a service with can read all data from a known template
6 | 18 | Value Converter |  | 1 | Create a service for converting string data into other type like boolean
6 | 19 | Implement data upload logic for Need Assessment and Referrals Template | 15,17,18 | 2 | Create services to map each row of data from a template to corresponding entity classes so that the data can be uploaded to database
7 | 20 | Design template data checker |  | 3 | Design the packages/classes structure for data checkers for different templates. Data checkers should be able to identify the errors that require human investigation and provide corresponding cell coordinates.Developers should follow SOLID design principle
7 | 21 | Create .property file for Need Assessment and Referrals Template | 20 | 1 | The .property file will contains the information about data error checking. eg. which columns can not be empty/null
7 | 22 | Configuration class for new property file | 21 | 1 | Create a corresponding configuration class for the new .property file for Need Assessment and Referrals Template
7 | 23 | Check not null cell | 22 | 1 | Add method to check whether the necessary cell contains no value.
7 | 24 | Implement Data checker for Needs Assessment and Referrals template | 23 | 2 | Implement a data checker for "Needs Assessment and Referrals Service" template
7 | 25 | Update upload_result view for update status |  | 1 | Update upload_result view so that it can show which cells contain errors that need human investigation; or display upload succeed when data successfully uploaded to database