## Sheet1
User Story | Task Number | Name | Dependency | Story Points | Description
1 | 1 | Create Project Skeleton |  | 1 | Create the Spring Boot Web application skeleton
1 | 2 | Design database for user | 1 | 2 | Design database schema for user credentials and roles
1 | 3 | Connecting to the database | 2 | 1 | Add mongoDB required dependency and configuration. Add corresponding Document classes for read and save data.
1 | 4 | Create dummy login accounts | 2 | 1 | Add test accounts for agency staff, TEQ staff and UTSC staff so that we can test the functionality of each user privilege.
1 | 5 | Create welcome page |  | 1 | Create a welcome page for the system as the start page of the application. User can trigger login in this page.
1 | 6 | Create a dashboard |  | 5 | Create a dashboard skeleton where users can see tags for available features. e.g file upload, create/modify login account, report generation
1 | 7 | Agency staff login |  | 5 | Add controller for login process. Add logic for Agency staff login so that file submission tag will be displayed in dashboard if login succeeded, the welcome page will be displayed if login failed
2 | 8 | TEQ staff login |  | 2 | Add logic for TEQ staff login so that tags for create/modify login accounts and report generation will be displayed in dashboard if login succeeded, the welcome page will be displayed if login failed
3 | 9 | UTSC staff login |  | 2 | Add logic for UTSC staff login so that tags for all features will be displayed in dashboard if login succeeded, the welcome page will be displayed if login failed
4 | 10 | File select UI | 6 | 2 | Add file selection form in the dashboard for the TEQ staff
5 | 11 | Create a Submit button for file upload | 6 | 2 | Add a button which can trigger file uploading after user selected file
5 | 12 | Integrate an Excel Processor to the codebase |  | 1 | Add dependency for Apache POI file processor
5 | 13 | Create method for template recognition | 12 | 8 | Design a method to recognize the type of the submitted template
5 | 14 | Create a User Logout button | 6 | 2 | Add a button that allows the user to logout and terminate their session.
6 | 15 | Design database for newcomer |  | 5 | Design and add collections for newcomer and data in iCare template
6 | 16 | Document classes for newcomer and template | 15 | 2 | Create corresponding document classes for user
6 | 17 | File error checking | 13 | 5 | Create logic to receive file uploaded, read data from the file, and put data into database